## Common
No. | Items | Start date | End date (PLAN) | End date (ACTUAL) | PIC | Status | Review date | Remark | 2017-05-05 | 2017-05-06 | 2017-05-07 | 2017-05-08 | 2017-05-09 | 2017-05-10 | 2017-05-11 | 2017-05-12
1 | Evaluation project overview | 2017-05-05 | 2017-05-09 | 2017-05-09 | Nhi-Thai | Done | 2017-05-09
2 | Development process overview | 2017-05-08 | 2017-05-09 | 2017-05-09 | Nhi-Thai | Done | 2017-05-09
3 | Templates used in project | 2017-05-08 | 2017-05-09 | 2017-05-09 | Nhi-Thai | Done | 2017-05-09
4 | SVN | 2017-05-08 | 2017-05-10 |  | Nhi-Thai |  |  |  | 2017-05-06: meeting
4.1 | . Introduce States of file/folder (non-version, added, etc.) | 2017-05-08 | 2017-05-09 |  | Nhi | In progress | 9-May 10-May | pre/pos condition
4.2 | . Introduce Repository | 2017-05-08 | 2017-05-09 |  | Nhi | In progress |  | AI: Replace "show log" discribe image by "repository" discribe image.
4.3 | . Introduce Working copy | 2017-05-08 | 2017-05-09 | 2017-05-09 | Nhi | Done | 2017-05-10
4.4 | . Introduce Branch | 2017-05-08 | 2017-05-09 | 2017-05-10 | Thai | Done | 2017-05-10
4.5 | . Introduce Tag | 2017-05-08 | 2017-05-09 | 2017-05-10 | Thai | Done | 2017-05-10
4.6 | . Functionality - Show log | 2017-05-08 | 2017-05-09 |  | Nhi | In progress | 2017-05-10 | AI: Change to a correct image to show more information about subversion and others.
4.7 | . Functionality - Repo-browser | 2017-05-08 | 2017-05-09 | 2017-05-10 | Nhi | Done | 2017-05-10
4.8 | . Functionality - Check for modification | 2017-05-08 | 2017-05-09 | 2017-05-10 | Nhi | Done | 2017-05-10
4.9 | . Functionality - Revision graph | 2017-05-08 | 2017-05-09 |  | Nhi | In progress | 2017-05-10
4.1 | . Functionality - Resolved… | 2017-05-08 | 2017-05-09 |  | Nhi | In progress | 2017-05-10
4.11 | . Functionality - Update to revision… | 2017-05-08 | 2017-05-09 | 2017-05-09 | Nhi | Done | 2017-05-10
4.12 | . Functionality - Rename… | 2017-05-08 | 2017-05-09 | 2017-05-09 | Nhi | Done | 2017-05-09
4.13 | . Functionality - Delete | 2017-05-08 | 2017-05-09 | 2017-05-09 | Nhi | Done | 2017-05-10
4.14 | . Functionality - Revert… | 2017-05-08 | 2017-05-09 | 2017-05-09 | Nhi | Done | 2017-05-10
4.15 | . Functionality - Clean up | 2017-05-08 | 2017-05-09 |  | Nhi | In progress | 2017-05-10
4.16 | . Functionality - Get lock… | 2017-05-08 | 2017-05-09 | 2017-05-09 | Nhi | Done | 2017-05-10
4.17 | . Functionality - Release lock | 2017-05-08 | 2017-05-09 | 2017-05-09 | Nhi | Done | 2017-05-10
4.18 | . Functionality - Branch/tag… | 2017-05-08 | 2017-05-09 | 2017-05-10 | Thai | Done | 2017-05-10
4.19 | . Functionality - Switch… | 2017-05-08 | 2017-05-09 | 2017-05-10 | Thai | Done | 2017-05-10
4.2 | . Functionality - Merge… | 2017-05-08 | 2017-05-09 |  | Thai | Not started |  | AI: Investigate when and how we use patch and merge, have more deep and exact
4.21 | . Functionality - Export… | 2017-05-08 | 2017-05-09 | 2017-05-10 | Thai | Done | 2017-05-10
4.22 | . Functionality - Relocate… | 2017-05-08 | 2017-05-09 | 2017-05-10 | Thai | Done | 2017-05-10
4.23 | . Functionality - Add… | 2017-05-08 | 2017-05-09 | 2017-05-09 | Thai | Done | 2017-05-10
4.24 | . Functionality - Create patch… | 2017-05-08 | 2017-05-09 |  | Thai | In progress | 2017-05-10 | AI: Investigate when and how we use patch and merge, have more deep and exact
4.25 | . Functionality - Apply patch… | 2017-05-08 | 2017-05-09 |  | Thai | Not started
4.26 | . Functionality - Settings | 2017-05-08 | 2017-05-09 | 2017-05-10 | Thai | Done
4.27 | . Abnormal cases - conflict | 2017-05-08 | 2017-05-09 |  | Thai | In progress | 9-May 10-May | AI: Make clear solving conflict option 3 in page 59. Show how to make this solving conflict option and add describe image
4.28 | . Abnormal case - locked | 2017-05-09 | 2017-05-10 |  | Thai | In progress | 2017-05-10
4.29 | . Abnormal case - unable to connect to repository | 2017-05-09 | 2017-05-10 |  | Nhi | In progress | 2017-05-10 | AI: Appear an abnormal case (repo graph's error) in this page, Nhi-san should add this case to "Abnormal cases" page (page 57)
4.3 | . Abnormal case - error in Revision graph | 2017-05-09 | 2017-05-10 |  | Nhi | In progress | 2017-05-10
Investigation notes: | [5 empty] | Not started
| For each functionality, please describe the following points: |  |  |  |  | In progress
| . What is it? |  |  |  |  | Done
| . How to use it? |  |  |  |  | -
. What is pre-condition of it (when is option enable)?
. What is pos-condition of it (what is result after option is applied)?
For each abnormal case, please describe the following points:
. Phenomenon
. Cause
. Solution
. Countermeasure
Review notes
2017-05-10 | Common comment: . Add precondition & postcondition in suitable pages. . Add more abnormal case and some describe images.

## IDE
No. | Items | Start date | End date (PLAN) | End date (ACTUAL) | PIC | Status | Review date | Remark | 2017-05-05 | 2017-05-06 | 2017-05-07 | 2017-05-08 | 2017-05-09 | 2017-05-10 | 2017-05-11 | 2017-05-12 | 2017-05-13 | 2017-05-14 | 2017-05-15 | 2017-05-16
1 | Set-up environment | 2017-05-05 | 2017-05-08 | 2017-05-08
1.1 | . e2 studio 5.4.0.014 | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08
1.2 | . KPIT GNUARM-NONE-EABI Toolchain | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08
1.3 | . KPIT GNURL78-ELF Toolchain | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08 |  | 2017-05-06: meeting
1.4 | . KPIT GNURX-ELF Toolchain | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08
1.5 | . KPIT GNUSH-ELF Toolchain | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08
1.6 | . Renesas CCRL Toolchain | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08
1.7 | . Renesas GCC for RL78 | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08
1.8 | . Renesas GCC for RX | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08
1.9 | . Renesas RXC Toolchain | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08
1.1 | . Renesas SHC Toolchain | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08
1.11 | . GNU Tools ARM Embedded | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08
1.12 | . CS+ and HEW | 2017-05-05 | 2017-05-08 | 2017-05-08 | Nhi-Thai | Done | 2017-05-08 | already done in basic training.
2 | Project management, Builder, e2 solution toolkit | 2017-05-11 | 2017-05-15
2.1 | . Project generator | 2017-05-11 | 2017-05-11 |  | Nhi | Done
2.1.1 | - Devices: RX, RL78, RZ, RH850, Synergy | 2017-05-11 | 2017-05-11 |  | Nhi | In progress
2.1.2 | - Toolchain: Renesas CC, Renesas GCC | 2017-05-11 | 2017-05-11 |  | Nhi | In progress
2.1.3 | - Project type: Executable, Library, Debug only | 2017-05-11 | 2017-05-11 |  | Nhi | In progress
2.2 | . Build configuration | 2017-05-11 | 2017-05-11 |  | Nhi | In progress
2.3 | . Buildtool settings | 2017-05-12 | 2017-05-12 |  | Nhi | In progress
2.3.1 | - Toolchain: CCRX | 2017-05-12 | 2017-05-12 |  | Nhi | In progress
2.3.2 | - Toolchain: GCC RL78 | 2017-05-12 | 2017-05-12 |  | Nhi | In progress
2.4 | . General view | 2017-05-15 | 2017-05-15 |  | Nhi | Not started
2.4.1 | - Error Log | 2017-05-15 | 2017-05-15 |  | Nhi | Not started
2.5 | . e2 solution toolkit views | 2017-05-15 | 2017-05-15 |  | Nhi | Not started
2.5.1 | - FIT Configuration | 2017-05-15 | 2017-05-15 |  | Nhi | Not started
2.5.2 | - Optimization Assistant | 2017-05-15 | 2017-05-15 |  | Nhi | Not started
2.5.3 | - Smart Browser | 2017-05-15 | 2017-05-15 |  | Nhi | Not started
2.5.4 | - Smart Manual | 2017-05-15 | 2017-05-15 |  | Nhi | Not started
3 | Debugger (Simulator/Emulator) | 2017-05-11 | 2017-05-15
3.1 | . Debug configuration | 2017-05-11 | 2017-05-11 |  | Thai | Done
3.2 | . Debugger views | 2017-05-11 | 2017-05-15 |  | Thai | Done
3.2.1 | - Breakpoints | 2017-05-11 | 2017-05-11 |  | Thai | Done
3.2.2 | - Current Consumption | 2017-05-11 | 2017-05-11 |  | Thai | In progress
3.2.3 | - Disassembly | 2017-05-11 | 2017-05-11 |  | Thai | Done
3.2.4 | - Eventpoints | 2017-05-12 | 2017-05-12 |  | Thai | In progress
3.2.5 | - Expressions | 2017-05-12 | 2017-05-12 |  | Thai | Done
3.2.6 | - IO Registers | 2017-05-12 | 2017-05-12 |  | Thai | Done
3.2.7 | - Memory | 2017-05-12 | 2017-05-12 |  | Thai | Done
3.2.8 | - Performance Analysis | 2017-05-12 | 2017-05-12 |  | Thai | In progress
3.2.9 | - Profile | 2017-05-12 | 2017-05-12 |  | Thai | In progress
3.2.10 | - Real-time Chart | 2017-05-15 | 2017-05-15 |  | Thai | Done
3.2.11 | - Registers | 2017-05-15 | 2017-05-15 |  | Thai | Done
3.2.12 | - Renesas Coverage | 2017-05-15 | 2017-05-15 |  | Thai | In progress
3.2.13 | - Trace | 2017-05-15 | 2017-05-15 |  | Thai | In progress
3.2.14 | - Variables | 2017-05-15 | 2017-05-15 |  | Thai | Done
3.2.15 | - Visual Expression | 2017-05-15 | 2017-05-15 |  | Thai | Done
Investigation notes: | [5 empty] | Not started
| References are the following: |  |  |  |  | In progress
| . IDE user manual |  |  |  |  | Done
| . e2_studio_v5.4_RT_PCL |  |  |  |  | -
. Former investigation (slides)

## Q&A
No. | Question | PIC | Date | Answer | PIC | Date | Status | Remark
1 | Had some issue when create debug configurator: 'Launching Test2 Debug' has encountered a problem. | Thai Ho | 15/05/2017 | Because of lack of output file when created project. | Thuy Tran | 15/05/2017 | Done
On progress
Done
-

## TestSkill
No. | Items | Start date | End date (PLAN) | End date (ACTUAL) | PIC | Status | Review date | Remark
Investigation notes: | [5 empty] | Not started
In progress
Done
-